## RICs
ID | Description | Type | Date Identified | Impact | Probability | Importance | Response | Owner | Closure Date
1001 | The data, planning, and execution information associated with the project leaked due to inadequate security. | Risk | 2020-01-24 | 10 | Very Low | 1 | Take all appropriate steps to make sure all sensitive material is protected with strong security measures. | Lewis Green
1002 | Project completion delayed due to lack of time management in team members. | Risk | 2020-01-24 | 50 | Low | 15 | Have team report progress regularly and provide means to report issues. | Lewis Green
1003 | Project completion delayed due to loss of team members from the project. | Risk | 2020-01-24 | 80 | Very Low | 8 | Give team members means to report personal issues and give support in response. | Lewis Green
1004 | Loss of project progress due to inadequate frequency/quality of backups. | Risk | 2020-01-24 | 90 | Low | 27 | Use version control systems such as GitHub and BitBucket to store progress securely. | Lewis Green
1005 | Progress slowed due to unclear or messy code, requiring explanation. | Risk | 2020-01-24 | 30 | Medium | 15 | All team members required to adhere to best coding practices. Use of such things as correct indentation, code comments, and white space. | Lewis Green
1006 | Progress slowed due to merge conflicts in the VCS. | Risk | 2020-01-24 | 20 | Medium | 10 | All team members should work on feature branches when coding, and merges to the development branch should be coordinated. | Lewis Green
1007 | Team loses focus on task due to other commitments. | Risk | 2020-02-05 | 40 | Medium | 20 | A structure is made with the need for time spent with other commitments in mind. | Lewis Green
1008 | Team members time is spent trying to achieve the wrong thing. | Risk | 2020-02-05 | 40 | Low | 12 | Regular team meetings and open communication channels allow team members to course correct should they start doing the wrong thing. | Lewis Green
1009 | Nuvven does not approve of Component Library used for UI design. | Risk | 2020-02-13 | 70 | Low | 21 | An argument will be made for the use of this library if needed. If not approved after discussion, an alternative will be found. | Lewis Green | 2020-02-18
1010 | Nuvven requests more features, stressing team members and extending required development time past what is possible. | Risk | 2020-02-17 | 70 | Medium | 35 | Use the agreed list of requirements prioritised with MoSCoW as a negotiation tool to either deny these changes or replace work. Make Nuvven aware that these changes will slow progress and make other backlog items less likely to be completed. | Lewis Green
1011 | Nuvven does not approve of prototypes at end of sprint, meaning the team will have to spend time fixing these problems. | Risk | 2020-02-18 | 80 | Low | 24 | Weekends can be used as overflow time, to fix any unexpected issues. Nuvven's expectations will be clearly defined in meetings to manage this problem. | Lewis Green
1012 | Nuvven does not provide access to their database due to issues on their end. This slows down development on team's end. | Issue | 2020-02-18 | 80 |  | 80 | Affected team members will do what relevant work they can and then turn their attention to other areas that they can do work on. This issue will close once Nuvven's API Gateway is fixed. | Lewis Green
1013 | Nuvven does not approve of other APIs/Libraries used for development. | Risk | 2020-02-18 | 60 | Low | 18 | Arguments will be made for the use of these, if not approved alternatives will be found in advance so no new research is needed. | Lewis Green
1014 | Nuvven's database which we work with could be subject to future difficulties, which will slow down the team's progress. | Risk | 2020-02-19 | 80 | Medium | 40 | PM will request a separate database for development use for the team. This would only be updated with secure updates. | Lewis Green
1015 | This mobile app is to be cross platform. The team has a lack of iOS devices to test the app on, which could mean the app will not work correctly on iOS devices. | Risk | 2020-02-19 | 70 | Low | 21 | Requests for iOS devices will be made to both Nuvven and to Napier contacts. | Lewis Green
1016 | Nuvven UI designer is responsible for supplying us with their desired look for each screen. Any delay in this will slow the team's work. | Risk | 2020-02-24 | 50 | Medium | 25 | We will continue to request these screens on a regular basis, and make plans that allow team members to do work without these. | Lewis Green
1017 | One team member away for the duration of sprint 2. Work may not be completed. | Risk | 2020-02-24 | 60 | Very Low | 6 | Away team member will do their best to complete assigned work and will collaborate with other team members to work around this. | Lewis Green