## Sheet1
7 Week Development Plan
Available Working Hours Per Week: 50 Hours
Product Backlog: | Item ID: | MoSCoW: | Description:
Login System | 1 | M | Login to system using username/email and password. Remember me option.
Reset password option, uses associated email to send resest link.
Dashboard and | 2 | M | Opening screen for users. Displays general information, and allows access to the
App Navigation |  |  | navigation bar.
Check Out Vehicle | 3 | M | Allows users to check vehicle out from work place. Select car to be delivered.
Check In Vehicle | 4 | M | Allows users to check vehicle in to work place after collection. Return selected car.
Deliver To Client | 5 | M | Allow users to mark a vehicle as delivered.
Collect From Client | 6 | M | Allow users to mark a vehicle as collected.
Update Cust. Info | 7 | M | Allow users to update stored customer information.
Display Cust. Info | 8 | M | Display relevant information of client for user to verify.
Display Location | 9 | M | Display location of car and user for collection and delivery purposes.
Record Images | 10 | M | Using phone camera, record images at collection and delivery times to verify car state. Allows
users to assess damage visually through photo comparison.
Display Notification | 11 | M | Send notifications to relevant users upon completion of tasks.
Take Payments | 12 | M | Take payment for damages and outstanding payments. Link with SaaS invoices.
Map Guide | 17 | S | Using location info and 3rd party APIs, display an interactable map to help users
locate delivery/collection locations.
Invoice Integration | 13 | S | Integrates payments made through the app into customer invoices in the SaaS platform.
Digital Signatures | 14 | S | Using 3rd party APIs, allow users to take customer signatures at delivery and collection.
Register Damages | 15 | C | Allow user to register damages viewed through photo comparison.
Assess Damages | 16 | C | Through damages registered, estimate the cost of the damages to the customers.
Each team member will dedicate an average of 8 hours of work every week to the project.
Development Cycle - Each Team Member Given Item From Product Backlog
PM assigned administrative work. Should teams need assistance, PM will assist.
Sprint | Team Members:
Week: | Lewis | Joe | Thomas | Zak | Hedwin
1 | Admin. | 2 | 2 | 1 | 1
2 | Admin. | 2 | 2 | 1 | 1
3 | Admin. | 5 | 5 | 3 | 3
4 | Admin. | 6 | 6 | 4 | 4
5 | Admin. | 9 | 9 | 7 | 7
6 | Admin. | 10 | 10 | 8 | 8
7 | Admin. | 11 | 11 | 12 | 12