## RICs
ID | Description | Type | Date Identified | Impact | Probability | Importance | Response | Owner | Closure Date
1001 | The data, planning, and execution information associated with the project leaked due to inadequate security. | Risk | 2020-01-24 | 10 | Very Low | 1 | Take all appropraite steps to make sure all sensitive material is protected with strong security measures. | Lewis Green
1002 | Project completion delayed due to lack of time management in team members. | Risk | 2020-01-24 | 50 | Low | 15 | Have team report progress regularly and provide means to report issues. | Lewis Green
1003 | Project completion delayed due to loss of team members from the project. | Risk | 2020-01-24 | 80 | Very Low | 8 | Give team members means to report personal issues and give support in response. | Lewis Green
1004 | Loss of project progress due to inadequate frequency/quality of backups. | Risk | 2020-01-24 | 90 | Low | 27 | Use version control systems such as GitHub to store progress securely. | Lewis Green
1005 | Progress slowed due to unclear or messy code, requiring explanation. | Risk | 2020-01-24 | 20 | Medium | 10 | All team members required to adhere to best coding practices. Use of such things as correct indentation, code comments, and white space. | Lewis Green
1006 | Progress slowed due to merge conflicts in the VCS. | Risk | 2020-01-24 | 20 | Medium | 10 | All team members should work on feature branches when coding, and merges to the development branch should be coordinated. | Lewis Green